## Sheet2
MCI Project Weekly Time Sheet
Team | OS1B | Student ID | 1155047 |  |  | Week starting: | 2025-03-31
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2025-03-31 | 12:00 | 15:00 | 3 | Reviewed Part 2 requirements and drafted milestone section | Initiates writing of Iteration Plan (Part 2) | Outlined milestone structure and deliverables
Tuesday | 2025-04-01 | 14:00 | 16:00 | 2 | Team meeting to discuss milestone scope, deliverables, and task schedule | Ensures alignment and input for Part 2 content | Finalized Milestone 1 scope with team consensus
Wednesday | 2025-04-02 | 8:30 | 10:00 | 1.5 | Team discussion on task breakdown, timeline, and role division | Collects content for Task Schedule and Team Roles sections | Tasks and timeline confirmed; ready to draft
Thursday | 2025-04-03 | 12:00 | 14:00 | 2 | Draft Done | Completes main timeline section of Part 2 | Schedule written, pending formatting, Roles clarified and reviewed with team
Thursday | 2025-04-03 | 15:30 | 16:30 | 1
Friday | 2025-04-04 | 11:00 | 18:00 | 7 | Wrote Communication Plan and finalized all Part 2 content | Matches required structure of Iteration Plan | Ready for proofreading and formatting
Saturday | 2025-04-05 | 14:00 | 18:00 | 4 | Research on LIWC & VADER | Study related information on the tasks | Ready for sentiment analysis by VADER
Sunday | 2025-04-06 | 14:00 | 16:00 | 2 | Final team sync and submission check | Week 5 final task before deadline | Submitted full Business Case with Part 2 included
|  |  | Total | 22.5