## Sheet2
MCI Project Weekly Time Sheet
Team | OS1B | Student ID | 1155047 |  |  | Week starting: | 2025-05-05
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2025-05-05 | 13:00 | 17:00 | 4 | Reviewed and edited Milestone 1 document (preparation for supervisor review) | Aligns with milestone documentation completion | Initial edits and notes prepared for Thursday walkthrough
Tuesday | 2025-05-06 | 12:00 | 15:00 | 3 | Refined frontend UI interactions and MVP layout | Improves UI responsiveness and usability as per milestone delivery plan | Prepared updated MVP version for supervisor review
Wednesday | 2025-05-07 | 12:00 | 14:00 | 2 | Logged feedback and began adjusting UI components accordingly | Front-end optimization initiated from live feedback | Refactor plan for homepage and results page created
Thursday | 2025-05-08 | 14:00 | 16:00 | 2 | Supervisor meeting: reviewed Milestone 1 and presented MVP demo | Synchronizes design and report quality with supervisor's expectations | Received detailed feedback on UI, documentation, and output interpretation
Thursday | 2025-05-08 | 15:30 | 16:30 | 1
Friday | 2025-05-09 | 11:00 | 15:00 | 4 | Revised Skills and LLM Output explanation in system + added MVP homepage content | Addresses supervisor's comments on clarity and user experience | Skill/LLM section explanations improved; homepage rewritten
Saturday | 2025-05-10 | 12:00 | 16:00 | 4 | Worked on README + initial draft of Product Manual | Supports documentation tasks mentioned in feedback | Setup steps and module-function mapping outlined
Sunday | 2025-05-11 | 15:00 | 19:00 | 4 | Began testing plan: embedded model performance review & drafted backend test outline | Initiates Week 9 testing focus; prepares framework for unit and UI testing discussions | Accuracy benchmarks logged; test strategy framework drafted
|  |  | Total | 24