## Sheet2
MCI Project Weekly Time Sheet
Team | OS1B | Student ID | 1155047 |  |  | Week starting: | 2025-05-12
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2025-05-12 | 10:00 | 13:00 | 5 | Reviewed supervisor’s feedback on Milestone 1 document | Aligns documentation quality with expectations | Identified needed changes for next version
Tuesday | 2025-05-13 | 12:00 | 15:00 | 3 | Drafted initial structure of Testing Plan (unit & UI tests, tools, metrics) | Supports Week 9 testing deliverable | Skeleton document ready; testing scope clarified
Wednesday | 2025-05-14 | 12:00 | 15:00 | 3 | Internal team meeting: discussed test plan focus and task division | Ensures alignment before implementation | Clarified responsibilities and shared implementation tasks
Thursday | 2025-05-15 | 11:00 | 12:00 | 1 | Compared performance of different embedding models (e.g., trivial inputs) | Supports Task 1 of test plan: algorithm performance evaluation | Accuracy impact documented; initial results included in plan
Thursday | 2025-05-15 | 14:00 | 16:00 | 2
Friday | 2025-05-16 | 11:00 | 15:00 | 4 | Developed backend unit test cases and integrated into test framework | Ensures module-level test coverage as per test plan | Unit test coverage implemented for major modules
Saturday | 2025-05-17 | 12:00 | 16:00 | 4 | Designed and executed frontend usability testing sessions | Validates interface quality; addresses UI validation strategy | Usability feedback collected, changes listed
Sunday | 2025-05-18 | 14:00 | 16:00 | 2 | Updated Testing Plan with results, tools used, strategy notes | Finalizes documentation for next team/supervisor review | Test plan draft completed; ready for review on May 22
|  |  | Total | 24