## Sheet2
MCI Project Weekly Time Sheet
Team | OS1B | Student ID | 1155047 |  |  | Week starting: | 2025-05-19
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2025-05-19 | 13:00 | 17:00 | 4 | Reviewed Testing Plan draft and identified open issues | Prepares for supervisor review | Questions and update notes prepared
Tuesday | 2025-05-20 | 12:00 | 15:00 | 3 | Refined diagrams and metrics section in draft | Improves technical clarity in test strategy | Improved pre-meeting version ready
Wednesday | 2025-05-21 | 12:00 | 14:00 | 2 | Practiced walkthrough of Testing Plan | Ensures smooth presentation during meeting | Aligned with teammates on key talking points
Thursday | 2025-05-22 | 11:00 | 12:00 | 1 | Supervisor meeting: walkthrough of Testing Plan, received feedback | Aligns QA direction with academic expectations | Supervisor suggested refinements on evaluation criteria
Thursday | 2025-05-22 | 14:00 | 16:00 | 2
Friday | 2025-05-23 | 11:00 | 15:00 | 4 | Applied feedback, rewrote conclusion and updated evaluation sections | Incorporates expert input into final version | Final review complete
Saturday | 2025-05-24 | 12:00 | 16:00 | 4 | Submitted final version of Testing Plan | Completes deliverable requirement | Document formally submitted
|  |  | Total | 20