## Sheet2
MCI Project Weekly Time Sheet
Team | OS1B | Student ID | 1155047 |  |  | Week starting: | 2025-05-26
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2025-05-26 | 13:00 | 17:00 | 4 | System testing (end-to-end) and logged initial functional issues | Ensures final system meets specifications and test coverage | Discovered multiple frontend rendering bugs; created issue list
Tuesday | 2025-05-27 | 12:00 | 15:00 | 3 | Fixed frontend logic bugs and revalidated LLM output rendering | Resolves functional gaps in user-facing interface | Improved result page logic and layout
Wednesday | 2025-05-28 | 12:00 | 14:00 | 2 | Conducted backend API testing and refined error handling | Ensures system robustness under various edge cases | Handled null values, timeout cases in API
Thursday | 2025-05-29 | 11:00 | 12:00 | 1 | Internal QA test + UI consistency review across all screens | Validates user experience consistency before handover | Supervisor suggested feedbacks on live demo and final report
Thursday | 2025-05-29 | 14:00 | 16:00 | 2
Friday | 2025-05-30 | 11:00 | 15:00 | 4 | Final regression testing and minor issue fixes | Confirms no regressions in core workflows | Passed 100% of defined test cases
Saturday | 2025-05-31 | 12:00 | 16:00 | 4 | Prepared final deliverables and packaging | Wraps up all artifacts for submission | README, manual, source code finalized
Sunday | 2025-06-01 | 12:00 | 16:00 | 4 | Submitted final product version | Marks official handover of product | Final submission completed on Github
|  |  | Total | 24