## Sheet2
MCI Project Weekly Time Sheet
Team | OS1B | Student ID | a1903948 |  |  | Week starting: | 2025-03-17
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025/3/17 | 8:00 | 12:00 | 4 | Read the paper mentioned in the supervisor's instructions related to the SVM classifier in NLP. | Provide conceptual knowledge for the implementation of the SVM classifier in Task 2. | Discuss and design the SVM classifier for Task 2.
Tuesday | 2025/3/18 | 23:00 | 14:00 | 3 | 1. Conduct an internal discussion on issues related to the implementation of Task 2 and details of the project execution process. Organize the questions before the workshop meeting to facilitate discussion with the supervisor. | A better organization and coordination for the completion of Task 2. | Label the type column of each question
Wednesday | 2025/3/19 | 17:00 | 23:00 | 6 | 1. Label the the 1-194 quesion manually 2.Discuss how to design svm classifier and other solution 3. Validate the classification accuracy of the SVM classifier. | For further data analysis | Compelet Task 2
Thursday | 2025/3/20 | 13:00 | 17:00 | 4 | 1.Discuss questions and task implementation details with the supervisor during the workshop. 2.Organize an internal discussion on how to address the shortcomings in Task 2 and the division of labor for the subsequent work. | Understand the shortcomings in the completion of Task 2 and the subsequent work required | Using BertTopic model to experiment topic modeling
Friday | 2025/3/21 | 13:00 | 5:00 | 4 | Read the official manual and related materials to learn about BERTTopic model | Finish Task 2 | Using the BERTopic model to complete topic modeling.
Saturday | 2025/3/22 | 13:00 | 16:00 | 5 | Codeing and complete the topic modeling of topics using the BERTopic model. | For futuer data analyse | Complete topic modeling and ready for futuer data analyse
|  |  | Total | 26