## Sheet2
MCI Project Weekly Time Sheet
Team | OS1B | Student ID | a1903948 |  |  | Week starting: | 2025-05-19
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025/5/19 | 12:00 | 16:00 | 4 | 1. Held another group discussion on the structure of the initial test draft. 2. Revised the test plan structure based on team feedback. | Prepare for test test plan | Completed initial draft of the testing plan
Tuesday | 2025/5/20 | 15:00 | 19:00 | 4 | 1.Executed part of the test cases based on the established test plan. | conducting test plan | Test cases executed.
Wednesday | 2025/5/21 | 12:00 | 18:00 | 6 | 1. Continued executing test cases and fixed bugs. | conducting test plan | Test cases executed.
Thursday | 2025/5/22 | 11:00 | 15:00 | 4 | 1. Discussed the draft test plan with the supervisor. | Prepare for test test plan | Final version of the test plan completed.
Friday | 2025/5/23 | 9:00 | 14:00 | 5 | 1. Held an group meeting to review missing and improvable elements in the test plan. 2. Revised the test report. | Prepare for test test plan | Final version of the test plan completed.
|  |  | Total | 23