## Sheet2
MCI Project Weekly Time Sheet
Team | OS1B | Student ID | a1903948 |  |  | Week starting: | 2025-05-26
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025/5/26 | 12:00 | 16:00 | 4 | 1. Continued executing test cases and fixed bugs. | conducting test plan | Test cases executed.
Tuesday | 2025/5/27 | 18:00 | 22:00 | 4 | 1. Continued executing test cases and fixed bugs. | conducting test plan | Test cases executed.
Wednesday | 2025/5/28 | 12:00 | 18:00 | 6 | 1. Held group discussion on how to present the live demo and structure the presentation slides. | Prepare for live demo presentation slides | conducting live demo presentation slids
Thursday | 2025/5/29 | 10:00 | 14:00 | 4 | 1. Structured the slide deck and started drafting the first version of the presentation slides. 2. Organized visual data and use case diagrams for slides. | Prepare for live demo presentation slides | conducting live demo presentation slids
Friday | 2025/5/30 | 12:00 | 18:00 | 6 | 1. Continued drafting and refining the live demo presentation slides. | Prepare for live demo presentation slides | conducting live demo presentation slids
|  |  | Total | 24