## Sheet2
MCI Project Weekly Time Sheet
Team | OS1B | Student ID | a1912958 |  |  | Week starting: | 2025-04-07
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? |  | Outcome/Next action
Monday | 2025-04-07 | 9:00 | 12:00 | 3 | Organize key functional points of the document, build the model - deployment environment; Participate in UI layout discussions and mark points for optimization. | Prepare for the backend MVP implementation; Promote the preliminary design of the front - end UI. |  | Completed the organization of key document functional points, and the model - deployment environment was initially built; UI layout discussions were fruitful, and points for optimization were marked for subsequent improvement.
Tuesday | 2025-04-08 | 13:00 | 16:00 | 3 | Split backend modules, debug integration code; Develop front - end component styles, test interactive functions. | Promote backend service modularization and integration; Support the implementation of front - end component functions. |  | Backend modules were split, and some integration code was debugged and passed; Front - end component styles were basically completed, and some bugs were found during the test of interactive functions, to be fixed.
Wednesday | 2025-04-09 | 10:00 | 13:00 | 3 | Participate in front - end and backend integration testing, optimize backend prompt words; Debug the connection between UI and mock data, organize the API list. | Ensure the normal docking of front - end and backend services; Prepare for subsequent docking with real APIs. |  | Some problems were found in the integration test, and progress was made in optimizing backend prompt words; The connection between UI and mock data was basically normal, and the API list was organized and to be confirmed.
Thursday | 2025-04-10 | 20:00 | 0:00 | 4 | Record meeting suggestions, sort out task allocation; Participate in synchronization meetings, organize meeting resolutions. | Clarify the follow - up optimization direction of the knowledge base; Make the team task priorities clearer. |  | Meeting suggestions were completely recorded, and task allocation was preliminarily sorted out; Meeting resolutions were organized, task priorities were updated, and progress as planned.
Friday | 2025-04-11 | 14:00 | 18:00 | 4 | Adjust backend division of labor, write test cases; Optimize UI interaction, test adaptive layout. | Promote the team to efficiently complete the MVP implementation; Improve the front - end user experience. |  | The backend division of labor was adjusted, and some test cases were written; UI interaction optimization was effective, and some compatibility problems were found in the test of the adaptive layout, to be solved.
Saturday | 2025-04-12 | 20:00 | 0:00 | 4 | Review problems, organize next - week tasks; Debug front - end rendering performance, review teammates' code. | Plan ahead for next - week's work; Ensure front - end code quality and performance. |  | Problems were reviewed, and the next - week task list was organized; Front - end rendering performance was improved, and teammates' code review was completed with some improvement suggestions.
|  |  | Total | 21