## Sheet2
MCI Project Weekly Time Sheet
Team | OS1B | Student ID | a1912958 |  |  | Week starting: | 2025-04-28
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? |  | Outcome/Next action
Monday | 2025-04-28 | 9:00 | 12:00 | 3 | Assist in researching the licensing and alternatives of sentiment - analysis tools and collect relevant materials; Participate in the review of the current UI logic, assist in learning front - end framework - related technologies, and organize learning materials. | Supported tool selection for the sentiment analysis module and facilitated MVP front-end optimization. |  | Completed preliminary data collection; identified cost issues with original tools; proposed UI improvement suggestions. Next: Finalize tool comparisons and deepen front-end learning.
Tuesday | 2025-04-29 | 13:00 | 17:00 | 4 | Participate in the research of large - scale sentiment models and organize model information; Assist in migrating the front - end from vanilla JS to React and solve basic problems. | Advanced model selection for sentiment analysis and drove front-end framework upgrades. |  | Summarized model pros/cons and application scenarios; made progress in codebase modularization. Next: Finalize model evaluation and complete migration.
Wednesday | 2025-04-30 | 10:00 | 13:00 | 3 | Assist in improving the preliminary test plan outline and supplement details; jointly study React knowledge, assist in understanding the manual service deployment on Azure, and prepare the basic environment. | Enhanced project testing plans and prepared for cloud deployment. |  | Completed a detailed test plan framework; set up basic Azure deployment environments. Next: Await test plan review and finalize deployment preparations.
Thursday | 2025-05-01 | 20:00 | 0:00 | 4 | Organized meeting feedback and initiated Milestone 1 documentation revisions. | Ensured alignment with project feedback and advanced documentation progress. |  | Recorded supervisor suggestions; began revising documentation based on meeting outcomes. Next: Finalize revisions and submit for team review.
Friday | 2025-05-02 | 14:00 | 18:00 | 4 | Completed Milestone 1 documentation revisions (format and technical details). Designed and revised data workflow and system flowcharts with team feedback. | Supported formal deliverables for Milestone 1 and prepared key visuals for reports. |  | Finalized documentation draft for review; approved flowcharts after revisions. Next: Incorporate team feedback and finalize charts.
Saturday | 2025-05-03 | 20:00 | 0:00 | 4 | Reviewed milestone content and charts for accuracy. Prepared a summary of sentiment analysis tool comparisons. | Ensured milestone deliverable quality and facilitated decision-making for tool selection. |  | Confirmed 80% completion of documentation; compiled a tool comparison summary. Next: Finalize documentation and schedule tool testing.
|  |  | Total | 22