## Sheet2
MCI Project Weekly Time Sheet
Team | OS1B | Student ID | a1912958 |  |  | Week starting: | 2025-05-05
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? |  | Outcome/Next action
Monday | 2025-05-05 | 9:00 | 12:00 | 3 | Assisted in implementing frontend code logic and conducted code review for optimization; Participated in designing data workflow diagrams. | Advanced MVP implementation and refined frontend functionality and visualization. |  | Completed partial code review and optimization suggestions; Initial framework of data workflow diagrams established. Next: Refine diagram elements and synchronize logic adjustments.
Tuesday | 2025-05-06 | 13:00 | 17:00 | 4 | Helped resolve frontend code styling conflicts and completed modular refactoring; Configured cloud server environments (Azure) for separate frontend-backend deployment; Attended team meetings to sync deployment progress and testing plan requirements. | Enhanced code maintainability, prepared for deployment, and aligned team objectives. |  | Styling conflicts resolved and modular refactoring completed; Cloud server configuration finished; Testing priorities clarified. Next: Initiate frontend-backend deployment and assist in designing test cases for similarity functions.
Wednesday | 2025-05-07 | 9:00 | 13:00 | 4 | Assisted in deploying frontend and backend separately on the cloud platform; Conducted frontend functionality testing and recorded anomalies; Reviewed and supplemented content for the Milestone 1 report. | Completed critical deployment, verified functionality, and improved milestone deliverables. |  | Frontend and backend successfully deployed; Functionality testing completed with issues recorded; Frontend deployment details added to the report. Next: Optimize service configurations and execute test cases.
Thursday | 2025-05-08 | 20:00 | 0:00 | 4 | Attended a mentor meeting to record feedback on the Milestone 1 report and adjusted the report structure. | Ensured the report met requirements and improved deliverable quality. |  | Mentor feedback recorded, report modification progress exceeded 50%; Outline for a new "Cloud Deployment Architecture" chapter drafted. Next: Finalize architecture diagrams and populate performance data.
Friday | 2025-05-09 | 14:00 | 18:00 | 4 | Performed frontend performance testing and generated optimization suggestions; Collaborated to finalize and archive the Milestone 1 report, and updated the testing plan Gantt chart. | Enhanced user experience, completed milestone delivery, and advanced testing plan visualization. |  | Performance data summarized and optimization suggestions submitted; Report finalized and uploaded, testing plan Gantt chart updated. Next: Track optimization progress and launch formal testing.
|  |  | Total | 19