## Sheet2
MCI Project Weekly Time Sheet
Team | OS1B | Student ID | a1912958 |  |  | Week starting: | 2025-05-12
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? |  | Outcome/Next action
Monday | 2025-05-12 | 10:00 | 13:00 | 3 | Assisted in reviewing the supervisor's feedback on the Milestone 1 document; Participated in the discussion on code - structure optimization and provided optimization suggestions; Assisted in the format adjustment of the internal dataset. | Helped improve the quality of the document to meet expectations; Contributed to the refactoring and optimization of the codebase; Prepared data for the model testing pipeline. |  | Identified the main modification directions of the document; Two code - optimization suggestions were adopted; Completed partial format adjustment of the dataset. Next: Follow up on the document - modification progress; Continuously monitor the implementation of code optimization; Complete the format adjustment of the dataset.
Tuesday | 2025-05-13 | 14:00 | 18:00 | 4 | Assisted in drafting the initial structure of the testing plan; Participated in the discussion on supplementing the data workflow and sorted out the data flow; Assisted in recording some indicators during the task of training models on internal data. | Supported the testing deliverables in Week 9; Optimized the project codebase structure; Assisted in the model - evaluation work. |  | Completed part of the framework content of the testing plan; Clarified the key links of the data workflow; The recorded indicators provided a basis for model evaluation. Next: Improve the details of the testing plan; Further improve the data workflow; Assist in analyzing model indicators.
Wednesday | 2025-05-14 | 9:00 | 13:00 | 4 | Participated in the internal team meeting on the testing plan and clarified the division of labor; Assisted in researching testing techniques and solutions and sorted out relevant materials; Assisted in analyzing the performance of models by category. | Ensured that the goals were aligned before implementation; Prepared for the testing plan; Gained an in - depth understanding of model performance. |  | Clarified personal tasks in the testing plan; Collected data on three testing techniques; Combed out the preliminary ideas for performance analysis. Next: Carry out the testing - plan work according to the division of labor; Further research on testing solutions; Improve the model - performance analysis.
Thursday | 2025-05-15 | 20:00 | 0:00 | 4 | Assisted in comparing the performance of different embedding models and recorded key data; Participated in the team discussion on the testing - plan strategy and put forward ideas; Assisted in generating and labeling some samples of the external dataset. | Supported the algorithm - performance evaluation task of the testing plan; Prepared for the testing plan; Created testing resources. |  | Recorded key performance data; Two ideas were discussed; Completed the labeling of some samples. Next: Assist in integrating model - performance data; Follow up on the determination of the testing - plan strategy; Complete the labeling of the external dataset.
Friday | 2025-05-16 | 14:00 | 18:00 | 4 | Assisted in developing backend unit - test cases; Assisted in outlining the structure of the testing documentation; Assisted in comparing the results during the external testing of the SVM model. | Ensured module - level test coverage; Prepared for the testing plan; Evaluated the generalization ability of the model. |  | Completed the development of some test cases; Initially determined the framework structure of the testing documentation; Recorded the differences in the results comparison. Next: Improve the backend unit - test cases; Refine the structure of the testing documentation; Assist in analyzing the model - generalization results.
|  |  | Total | 19