## Sheet2
MCI Project Weekly Time Sheet
Team | OS1B | Student ID | a1912958 |  |  | Week starting: | 2025-05-26
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? |  | Outcome/Next action
Monday | 2025-05-26 | 13:00 | 17:00 | 4 | Participated in end - to - end system testing and recorded initial functional issues; Assisted in drafting the initial version of the "Background & Objectives" section of the presentation. | Ensures the final system meets specifications and test coverage requirements; Clarifies the problem context and project motivation. |  | Next: Follow up on issue - fixing; Improve the relevant content of the presentation.
Tuesday | 2025-05-27 | 12:00 | 15:00 | 3 | Re-validated the large-language model output rendering; Started editing the basic structure of the final report. | Resolves functional gaps in the user - facing interface; Advances the progress of the final report. |  | Next: Continue to check the frontend functions; Continue to improve the report structure.
Wednesday | 2025-05-28 | 13:00 | 15:00 | 2 | Conducted backend API testing and optimized error handling; Participated in the group discussion on the presentation and structure of the live demo. | Ensures the robustness of the system under various edge cases; Prepares the presentation for the live demo. |  | Determined the structure and division of labor of the presentation. Next: Further test the backend API; Start creating the presentation.
Thursday | 2025-05-29 | 13:00 | 14:00 | 1 | Conducted internal QA testing and UI consistency review across all screens. | Validates the consistency of the user experience; Makes the implementation steps clear to the audience. |  | The supervisor provided feedback on the live demo and the final report; Completed part of the slide framework. Next: Improve according to the feedback; Continue to improve the slide content.
Friday | 2025-05-30 | 11:00 | 14:00 | 3 | Conducted final testing and fixed minor issues. | Confirms no bugs in core workflows. |  | Completed the first version of the responsible part of the PPT. Next: Await review; Prepare for the final revision of the presentation.
|  |  | Total | 13