## Sheet2
MCI Project Weekly Time Sheet
Team OS1B |  | Student ID a1909803 |  |  |  | Week starting: 7/4
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025-05-05 | 8:00 | 13:00 | 5 | Check the backend code carefully again to see if there are any inconsistencies with the teacher's communication | Improve the problems encountered in the last meeting | Found a detail problem and discussed it with team members
Tuesday | 2025-05-06 | 14:00 | 15:00 | 3 | Complete the code flow chart with team members | Improve the problems encountered in the last meeting | Have a clear flowchart
Wednesday | 2025-05-07 | 8:00 | 11:00 | 3 | Test the impact of different embedding methods on finding similar problems | Improve the problems encountered in the last meeting | It was found that different embeddings had an impact on the results.
Thursday | 2025-05-08 | 18:00 | 22:00 | 4 | Complete the comparison between Lanchain built-in method and cosine similarity method | push forward for testing plan | It is found that when the search type in Lanchain's built-in method is set to similarity, the documents found are consistent with those found by manually calculating the cosine similarity.
Friday | 2025-05-09 | 13:00 | 17:00 | 4 | Modify a classifier logic | Prepare for MVP Implementing | First determine whether the user's question is relevant, and if so, pass it to the classifier
Saturday | 2025-05-10 | 14:00 | 18:00 | 4 | Modify some document contents according to teacher's suggestion | Prepare for milestone1 report | Waiting for team members to confirm the final version
|  |  | Total | 23